## Slide 1: Chapter 12: Project Procurement Management
Information Technology Project Management, Seventh Edition
ĐẶNG THỊ THU HÀ – SE
dtthuha79@gmail.com
https://lms.iuh.edu.vn
.

## Slide 2: Learning Objectives
Understand the importance of project procurement management and the increasing use of outsourcing for information technology (IT) projects
Describe the work involved in planning procurements for projects, including determining the proper type of contract to use and preparing a procurement management plan, statement of work, source selection criteria, and make-or-buy analysis
Discuss how to conduct procurements and strategies for obtaining seller responses, selecting sellers, and awarding contracts

## Slide 3: Importance of Project Procurement Management
Procurement means acquiring goods and/or services from an outside source
Other terms include purchasing and outsourcing
Experts predict that global spending on computer software and services will continue to grow
People continue to debate whether offshore outsourcing helps their own country or not

## Slide 4: Contracts
A contract is a mutually binding agreement that obligates the seller to provide the specified products or services and obligates the buyer to pay for them
Contracts can clarify responsibilities and sharpen focus on key deliverables of a project
Because contracts are legally binding, there is more accountability for delivering the work as stated in the contract
A recent trend in outsourcing is the increasing size of contracts

## Slide 5: Project Procurement Management Processes
Project procurement management: Acquiring goods and services for a project from outside the performing organization
Processes include:
  Planning procurement management: Determining what to procure and when and how to do it
  Conducting procurements: Obtaining seller responses, selecting sellers, and awarding contracts
  Controlling procurements: Managing relationships with sellers, monitoring contract performance, and making changes as needed
  Closing procurements: Completing and settling each contract or agreement, including resolving of any open items

## Slide 6: Figure 12-1. Project Procurement Management Summary

## Slide 7: Planning Procurement Management
Identifying which project needs can best be met by using products or services outside the organization
If there is no need to buy any products or services from outside the organization, then there is no need to perform any of the other procurement management processes

## Slide 8: Types of Contracts
Different types of contracts can be used in different situations:
  Fixed price or lump sum contracts: Involve a fixed total price for a well-defined product or service
  Cost reimbursable contracts: Involve payment to the seller for direct and indirect costs
  Time and material contracts: Hybrid of both fixed price and cost reimbursable contracts, often used by consultants
  Unit price contracts: Require the buyer to pay the seller a predetermined amount per unit of service
A single contract can actually include all four of these categories, if it makes sense for that particular procurement

## Slide 9: Point of Total Assumption
The Point of Total Assumption (PTA) is the cost at which the contractor assumes total responsibility for each additional dollar of contract cost
Contractors do not want to reach the point of total assumption, because it hurts them financially, so they have an incentive to prevent cost overruns
The PTA is calculated with the following formula:
PTA = (ceiling price – target price)/buyer share + target cost

## Slide 10
Fixed Price Contract includes:
  FP (Firm Fixed Price Contract)
  FPIF (Fixed Price Incentive Fee Contract)
  FP-EPA (Fixed Price with Economic Price Adjusment Contract)

## Slide 11: Cost Reimbursable Contracts
Cost plus incentive fee (CPIF): The buyer pays the supplier for allowable performance costs plus a predetermined fee and an incentive bonus
Cost plus fixed fee (CPFF): The buyer pays the supplier for allowable performance costs plus a fixed fee payment usually based on a percentage of estimated costs
Cost plus percentage of costs (CPPC): The buyer pays the supplier for allowable performance costs plus a predetermined percentage based on total costs

## Slide 12: Figure 12-2. Contract Types Versus Risk

## Slide 13: Media Snapshot
Contract incentives can be extremely effective. On August 1, 2007, tragedy struck Minneapolis, Minnesota, when a bridge on I-35W collapsed, killing 13 motorists, injuring 150 people, and leaving a mass of concrete and steel in the river and on its banks
Peter Sanderson, project manager for the joint venture of Flatiron-Manson led his team in completing the project. The contractors earned $25 million in incentive fees on top of their $234 million contract for completing the bridge three months ahead of schedule
MnDOT justified the incentive payment by saying that each day the bridge was closed it cost road users more than $400,000

## Slide 14: Contract Clauses
Contracts should include specific clauses to take into account issues unique to the project
Can require various educational or work experience for different pay rights
A termination clause is a contract clause that allows the buyer or supplier to end the contract

## Slide 15: Tools and Techniques for Planning Purchases and Acquisitions
Expert judgment
Market research
Make-or-buy analysis: General management technique used to determine whether an organization should make or perform a particular product or service inside the organization or buy from someone else

## Slide 16: Make-or-Buy Example
Assume you can lease an item you need for a project for $800/day. To purchase the item, the cost is $12,000 plus a daily operational cost of $400/day
How long will it take for the purchase cost to be the same as the lease cost?

## Slide 17: Make-or Buy Solution
Set up an equation so both options, purchase and lease, are equal
In this example, use the following equation. Let d be the number of days to use the item:
  $12,000 + $400d = $800d
  Subtracting $400d from both sides, you get:
  $12,000 = $400d
  Dividing both sides by $400, you get:
  d = 30
If you need the item for more than 30 days, it is more economical to purchase it

## Slide 18: Procurement Management Plan
Describes how the procurement processes will be managed, from developing documentation for making outside purchases or acquisitions to contract closure
Contents varies based on project needs

## Slide 19: Contract Statement of Work (SOW)
A statement of work is a description of the work required for the procurement
If a SOW is used as part of a contract to describe only the work required for that particular contract, it is called a contract statement of work
A SOW is a type of scope statement
A good SOW gives bidders a better understanding of the buyer’s expectations

## Slide 20: Figure 12-3. Statement of Work (SOW) Template

## Slide 21: Procurement Documents
Request for Proposals: Used to solicit proposals from prospective sellers
  A proposal is a document prepared by a seller when there are different approaches for meeting buyer needs
Requests for Quotes: Used to solicit quotes or bids from prospective suppliers
  A bid, also called a tender or quote (short for quotation), is a document prepared by sellers providing pricing for standard items that have been clearly defined by the buyer

## Slide 22: Figure 12-4. Request for Proposal (RFP) Template

## Slide 23: Source Selection Criteria
It’s important to prepare some form of evaluation criteria, preferably before issuing a formal RFP or RFQ
Beware of proposals that look good on paper; be sure to evaluate factors, such as past performance and management approach
Can require a technical presentation as part of a proposal

## Slide 24: Conducting Procurements
Deciding whom to ask to do the work
Sending appropriate documentation to potential
sellers
Obtaining proposals or bids
Selecting a seller
Awarding a contract

## Slide 25: Approaches for Procurement
Organizations can advertise to procure goods and services in several ways:
  Approaching the preferred vendor
  Approaching several potential vendors
  Advertising to anyone interested
A bidders’ conference can help clarify the buyer’s expectations

## Slide 26: Figure 12-5. Sample Proposal Evaluation Sheet

## Slide 27: Seller Selection
Organizations often do an initial evaluation of all proposals and bids and then develop a short list of potential sellers for further evaluation
Sellers on the short list often prepare a best and final offer (BAFO)
Final output is a contract signed by the buyer and the selected seller

## Slide 28: Controlling Procurements
Ensures that the seller’s performance meets contractual requirements
Contracts are legal relationships, so it is important that legal and contracting professionals be involved in writing and administering contracts
It is critical that project managers and team members watch for constructive change orders, which are oral or written acts or omissions by someone with actual or apparent authority that can be construed to have the same effect as a written change order

## Slide 29: Suggestions for Change Control in Contracts
Changes to any part of the project need to be reviewed, approved, and documented by the same people in the same way that the original part of the plan was approved
Evaluation of any change should include an impact analysis. How will the change affect the scope, time, cost, and quality of the goods or services being provided?
Changes must be documented in writing. Project team members should also document all important meetings and telephone phone calls

## Slide 30: Suggestions for Change Control in Contracts (cont’d)
Project managers and teams should stay closely involved to make sure the new system will meet business needs and work in an operational environment
Have backup plans
Use tools and techniques, such as a contract change control system, buyer-conducted performance reviews, inspections and audits, and so on

## Slide 31: Closing Procurements
Involves completing and settling contracts and resolving any open items
The project team should:
    Determine if all work was completed correctly and satisfactorily
    Update records to reflect final results
    Archive information for future use
The contract itself should include requirements for formal acceptance and closure

## Slide 32: Tools to Assist in Contract Closure
Procurement audits identify lessons learned in the procurement process
Negotiated settlements help close contracts more smoothly
A records management system provides the ability to easily organize, find, and archive procurement-related documents

## Slide 33: Chapter Summary
Project procurement management involves acquiring goods and services for a project from outside the performing organization
Processes include:
  Plan procurement management
  Conduct procurements
  Control procurements
  Close procurements