## Slide 1: Chapter 2: The Project Management and Information Technology Context
Information Technology Project Management, Seventh Edition
Note: See the text itself for full citations.

## Slide 2: Learning Objectives
Describe the systems view of project management and how it applies to information technology (IT) projects
Understand organizations, including the four frames, organizational structures, and organizational culture
Explain why stakeholder management and top management commitment are critical for a project’s success

## Slide 3: Learning Objectives
Understand the concept of a project phase and the project life cycle, and distinguish between project development and product development
Discuss the unique attributes and diverse nature of IT projects
Describe recent trends affecting IT project management, including globalization, outsourcing, virtual teams, and agile project management
Notes: diverse : phong phú, đa dạng

## Slide 4: Projects Cannot Be Run In Isolation
Projects must operate in a broad organizational environment
Project managers need to use systems thinking:
  taking a holistic view of carrying out projects within the context of the organization
Senior managers must make sure projects continue to support current business needs
Notes: Isolation: độc lập

## Slide 5: A Systems View of Project Management
A systems approach emerged in the 1950s to describe a more analytical approach to management and problem solving
Three parts include:
  Systems philosophy: an overall model for thinking about things as systems
  Systems analysis: problem-solving approach
  Systems management: address business, technological, and organizational issues before making changes to systems

## Slide 6: Figure 2-1. Three Sphere Model for Systems Management

## Slide 7: Figure 2-2. Perspectives on Organizations
Notes: Perspectives on Organizations: Quan điểm về tổ chức
Coalition: liên minh
Issue=problem
Harmony: hòa hợp

## Slide 8: What Went Wrong?
In a paper titled “A Study in Project Failure,” two researchers examined the success and failure of 214 IT projects over an eight-year period in several European countries.
The researchers found that only one in eight (12.5 percent) were considered successful in terms of meeting scope, time, and cost goals.
The authors said that the culture within many organizations is often to blame
Among other things, people often do not discuss important leadership, stakeholder, and risk management issues

## Slide 9: Organizational Structures
3 basic organization structures
  Functional: functional managers report to the CEO
  Project: program managers report to the CEO
  Matrix: middle ground between functional and project structures; personnel often report to two or more bosses; structure can be weak, balanced, or strong matrix

## Slide 10: Figure 2-3. Functional, Project, and Matrix Organizational Structures
Notes: Chief executive officer

## Slide 11: Table 2-1. Organizational Structure Influences on Projects

## Slide 12: Thiết lập công ty theo mô hình:
Functional: Chức năng
Project: Bao nhiêu người QL, Lĩnh vực QL?
Matrix: Phân cấp QL

## Slide 13: Organizational Culture
Organizational culture is a set of shared assumptions, values, and behaviors that characterize the functioning of an organization
Many experts believe the underlying causes of many companies’ problems are not the structure or staff, but the culture

## Slide 14: Ten Characteristics of Organizational Culture
Member identity*
Group emphasis*
People focus
Unit integration*
Control
Risk tolerance*
Reward criteria*
Conflict tolerance*
Means-ends orientation
Open-systems focus*
*Project work is most successful in an organizational culture where these items are strong/high and other items are balanced.

## Slide 15: Stakeholder Management
Project managers must take time to identify, understand, and manage relationships with all project stakeholders
Using the four frames of organizations can help meet stakeholder needs and expectations
Senior executives/top management are very important stakeholders
See Chapter 13, Project Stakeholder Management, for more information

## Slide 16: Media Snapshot
The media have often reported on mismanaged IT projects. A classic example and popular case study is the baggage handling system at Denver International Airport (DIA).
The system was supposed to reduce flight delays, shorten waiting times at luggage carousels, and save money, but instead it caused huge problems.
One important reason for this famous project disaster was the failure to recognize the project’s complexity.
Notes: Media Snapshot: truyền thông

## Slide 17: The Importance of Top Management Commitment
People in top management positions are key stakeholders in projects
A very important factor in helping project managers successfully lead projects is the level of commitment and support they receive from top management
Without top management commitment, many projects will fail.
Some projects have a senior manager called a champion who acts as a key proponent for a project.
Notes: Commitment: cam kết

## Slide 18: How Top Management Can Help Project Managers
Providing adequate resources
Approving unique project needs in a timely manner
Getting cooperation from other parts of the organization
Mentoring and coaching on leadership issues

## Slide 19: Best Practice
IT governance addresses the authority and control for key IT activities in organizations, including IT infrastructure, IT use, and project management
A lack of IT governance can be dangerous, as evidenced by three well-publicized IT project failures in Australia (Sydney Water’s customer relationship management system, the Royal Melbourne Institute of Technology’s academic management system, and One.Tel’s billing system)

## Slide 20: Need for Organizational Commitment to Information Technology (IT)
If the organization has a negative attitude toward IT, it will be difficult for an IT project to succeed
Having a Chief Information Officer (CIO) at a high level in the organization helps IT projects
Assigning non-IT people to IT projects also encourage more commitment

## Slide 21: Need for Organizational Standards
Standards and guidelines help project managers be more effective
Senior management can encourage
  the use of standard forms and software for project management
  the development and use of guidelines for writing project plans or providing status information
  the creation of a project management office or center of excellence

## Slide 22: Project Phases and the Project Life Cycle
A project life cycle is a collection of project phases that defines
  what work will be performed in each phase
  what deliverables will be produced and when
  who is involved in each phase, and
  how management will control and approve work produced in each phase
A deliverable is a product or service produced or provided as part of a project
Notes: project phase: giai đoạn DA

## Slide 23: More on Project Phases
In early phases of a project life cycle
  resource needs are usually lowest
  the level of uncertainty (risk) is highest
  project stakeholders have the greatest opportunity to influence the project
In middle phases of a project life cycle
  the certainty of completing a project improves
  more resources are needed
The final phase of a project life cycle focuses on
  ensuring that project requirements were met
  the sponsor approves completion of the project

## Slide 24: Figure 2-4. Phases of the Traditional Project Life Cycle

## Slide 25: Product Life Cycles
Products also have life cycles
The Systems Development Life Cycle (SDLC) is a framework for describing the phases involved in developing and maintaining information systems
Systems development projects can follow
  Predictive life cycle: the scope of the project can be clearly articulated and the schedule and cost can be predicted
  Adaptive Software Development (ASD) life cycle: requirements cannot be clearly expressed, projects are mission driven and component based, using time-based cycles to meet target dates

## Slide 26: Predictive Life Cycle Models
Waterfall model: has well-defined, linear stages of systems development and support
Spiral model: shows that software is developed using an iterative or spiral approach rather than a linear approach
Incremental build model: provides for progressive development of operational software
Prototyping model: used for developing prototypes to clarify user requirements
Rapid Application Development (RAD) model: used to produce systems quickly without sacrificing quality

## Slide 27: Figure 2-5. Waterfall and Spiral Life Cycle Models

## Slide 28: Agile Software Development
Agile software development has become popular to describe new approaches that focus on close collaboration between programming teams and business experts
See the last section of this chapter and Chapter 3 for more information on agile

## Slide 29: The Importance of Project Phases and Management Reviews
A project should successfully pass through each of the project phases in order to continue on to the next
Management reviews, also called phase exits or kill points, should occur after each phase to evaluate the project’s progress, likely success, and continued compatibility with organizational goals

## Slide 30: What Went Right?
"The real improvement that I saw was in our ability toin the words of Thomas Edisonknow when to stop beating a dead horse.…Edison's key to success was that he failed fairly often; but as he said, he could recognize a dead horse before it started to smell...In information technology we ride dead horsesfailing projectsa long time before we give up. But what we are seeing now is that we are able to get off them; able to reduce cost overrun and time overrun. That's where the major impact came on the success rate.”*
Many organizations, like Huntington Bancshares, Inc., use an executive steering committee to help keep projects on track.
*Cabanis, Jeannette, "'A Major Impact': The Standish Group's Jim Johnson On Project Management and IT Project Success," PM Network, PMI, Sep.1998, p. 7

## Slide 31: The Context of IT Projects
IT projects can be very diverse in terms of size, complexity, products produced, application area, and resource requirements
IT project team members often have diverse backgrounds and skill sets
IT projects use diverse technologies that change rapidly. Even within one technology area, people must be highly specialized

## Slide 32: Recent Trends Affecting IT Project Management
Globalization
Outsourcing: Outsourcing is when an organization acquires goods and/or sources from an outside source. Offshoring is sometimes used to describe outsourcing from another country
Virtual teams: A virtual team is a group of individuals who work across time and space using communication technologies
Agile project management

## Slide 33: Important Issues and Suggestions Related to Globalization
Issues
  Communications
  Trust
  Common work practices
  Tools
Suggestions
  Employ greater project discipline
  Think global but act local
  Keep project momentum going
  Use newer tools and technology

## Slide 34: Outsourcing
Organizations remain competitive by using outsourcing to their advantage, such as finding ways to reduce costs
Their next challenge is to make strategic IT investments with outsourcing by improving their enterprise architecture to ensure that IT infrastructure and business processes are integrated and standardized (See Suggested Readings)
Project managers should become more familiar with negotiating contracts and other outsourcing issues

## Slide 35: Global Issues
Outsourcing also has disadvantages. For example, Apple benefits from manufacturing products in China, but it had big problems there after its iPhone 4S launch in January 2012 caused fighting between migrant workers who were hired by scalpers to stand in line to buy the phones.
When Apple said it would not open its store in Beijing, riots resulted and people attacked security guards. The Beijing Apple Store has had problems before. In May 2011, four people were injured when a crowd waiting to buy the iPad 2 turned ugly.

## Slide 36: Virtual Teams Advantages
Increasing competiveness and responsiveness by having a team of workers available 24/7
Lowering costs because many virtual workers do not require office space or support beyond their home offices.
Providing more expertise and flexibility by having team members from across the globe working any time of day or night
Increasing the work/life balance for team members by eliminating fixed office hours and the need to travel to work.

## Slide 37: Virtual Team Disadvantages
Isolating team members
Increasing the potential for communications problems
Reducing the ability for team members to network and transfer information informally
Increasing the dependence on technology to accomplish work
See text for a list of factors that help virtual teams succeed, including team processes, trust/relationships, leadership style, and team member selection

## Slide 38: Agile Project Management
Agile means being able to move quickly and easily, but some people feel that project management, as they have seen it used, does not allow people to work quickly or easily.
Early software development projects often used a waterfall approach, as defined earlier in this chapter. As technology and businesses became more complex, the approach was often difficult to use because requirements were unknown or continuously changing.
Agile today means using a method based on iterative and incremental development, in which requirements and solutions evolve through collaboration.

## Slide 39: Agile Project Management

## Slide 40: Agile Software Development
“Agile Software Development is an umbrella term for a set of methods and practices based on the values and principles expressed in the Agile Manifesto.
Solutions evolve through collaboration between self-organizing, cross-functional teams utilizing the appropriate practices for their context.”
Notes: Agile Software Develoopment là một thuật ngữ dùng để mô tả một tập hợp các phương thức và thực hành dựa trên các giá trị và các nguyên lý được nêu ra trong tuyên ngôn Agile.
Các phương pháp tiến triển thông qua sự kết hợp của team tự quản và team xuyên chức năng bằng cách sử dụng các phương pháp phù hợp cho bối cảnh của họ.

## Slide 41: Agile Makes Sense for Some Projects, But Not All
Many seasoned experts in project management warn people not to fall for the hype associated with Agile.
For example, J. Leroy Ward, Executive Vice President at ESI International, said that “Agile will be seen for what it is … and isn’t….Project management organizations embracing Agile software and product development approaches will continue to grow while being faced with the challenge of demonstrating ROI through Agile adoption.”*
*J. Leroy Ward, “The Top Ten Project Management Trends for 2011,” projecttimes.com
(January 24, 2011).
Notes: Sense: giác quan

## Slide 42: Manifesto for Agile Software Development
In February 2001, a group of 17 people that called itself the Agile Alliance developed and agreed on the Manifesto for Agile Software Development, as follows:
“We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan”*
*Agile Manifesto, www.agilemanifesto.org.
Notes: Manifesto : tuyên ngôn

## Slide 43: Scrum
According to the Scrum Alliance, Scrum is the leading agile development method for completing projects with a complex, innovative scope of work.
The term was coined in 1986 in a Harvard Business Review study that compared high-performing, cross-functional teams to the scrum formation used by rugby teams.
Notes: Scrum AllianceⓇ is a nonprofit organization that is guiding and inspiring individuals, leaders, and organizations with agile practices, principles, and values to help create workplaces that are joyful, prosperous, and sustainable. [https://www.scrumalliance.org/]
joyful, prosperous, and sustainable: vui vẻ, thịnh vượng và bền vững.

## Slide 44: Figure 2-6. Scrum Framework

## Slide 45: Agile, the PMBOK® Guide, and a New Certification
The PMBOK® Guide describes best practices for what should be done to manage projects.
Agile is a methodology that describes how to manage projects.
The Project Management Institute (PMI) recognized the increased interest in Agile, and introduced a new certification in 2011 called Agile Certified Practitioner (ACP).
Seasoned project managers understand that they have always had the option of customizing how they run projects, but that project management is not easy, even when using Agile.

## Slide 46: Chapter Summary
Project managers need to take a systems approach when working on projects
Organizations have four different frames: structural, human resources, political, and symbolic
The structure and culture of an organization have strong implications for project managers
Projects should successfully pass through each phase of the project life cycle
Project managers need to consider several factors due to the unique context of information technology projects
Recent trends affecting IT project management include globalization, outsourcing, virtual teams, and Agile